## Automatic Gantt Chart
Copy this file to edit this chart. Go to File, the select "Make a Copy". Please don't Request Access
| Build Gantt Charts Easily with Instagantt | [11 empty] | Build Gantt Charts Easily with Instagantt
Tasks | Progress | Start | Expected End | Start on Week | Expected duration | User | Estimated Hours | Actual Hours | Estimated Cost | Actual Cost | Priority | Risk
Project Definition Document | 0% | 2021-08-02 | 22/2/2021 | 0 | 2 |  | 25 | 28 |  |  | 5 | 4
Topic Background Research | 0% | 22/2/2021 | 2021-08-03 | 2 | 4 | Alexandra Cuartin | 15 | 20 |  |  | 5 | 4
[6 empty] | Victor Pascow | 10 | 8 |  |  | 5
----- Datasets ----- | [6 empty] | 95 | 84 | 1600 | 1550 | 4 | 2
Dataset Investigation | 0% | 15/3/2021 | 29/3/2021 | 5 | 2 | Victor Pascow | 2 | 2 |  |  | 4 | 2
Dataset Selection | 0% | 29/3/2021 | 2021-05-04 | 7 | 1 | Wendy Torrance | 48 | 40 | 500 | 450 | 3 | 2
Dataset Cleaning / Merging | 0% | 2021-05-04 | 2021-12-04 | 8 | 1 | Alexandra Cuartin | 45 | 42 | 300 | 325 | 2 | 1
[6 empty] | Wendy Torrance |  |  | 800 | 775 | 5 | 2
----- Model ----- | [6 empty] | 112 | 98 | 350 | 250 | 4 | 3
Build A Hate Speech Classification Model | 0% | 2021-12-04 | 2021-07-06 | 9 | 8 | Alexandra Cuartin | 72 | 72 | 350 | 250 | 5 | 5
Expand Model To Include Subclasses | 0% | 2021-03-05 | 28/6/2021 | 12 | 8 | Laurie Strode | 36 | 24 |  |  | 3 | 3
Evaluate Model | 0% | 2021-12-04 | 28/6/2021 | 9 | 11 | Alexandra Cuartin | 4 | 2 |  |  | 5 | 1
----- Final Report ----- | [6 empty] | 28 | 28 |  |  | 4
Abstract | 0% | 19/4/2021 | 17/5/2021 | 10 | 4 | Andy Barclay | 5 | 4 |  |  | 5
Introduction | 0% | 17/5/2021 | 31/5/2021 | 14 | 2 | Wendy Torrance | 10 | 10 |  |  | 5
Background / Related Work | 0% | 22/3/2021 | 28/6/2021 | 6 | 14 | Alexandra Cuartin | 10 | 12 |  |  | 5
Methodology | 0% | 2021-12-04 | 2021-05-07 | 9 | 12 | Alexandra Cuartin | 1 | 0.5 |  |  | 2
Experiments / Results | 0% | 21/6/2021 | 19/7/2021 | 19 | 4 | Jason Myers | 1 | 1 |  |  | 5
Conclusion / Future Work | 0% | 28/6/2021 | 19/7/2021 | 20 | 3 | Alexandra Cuartin | 1 | 0.5 |  |  | 3
----- Viva Prep ----- | [6 empty] | 53 | 50 | 855 | 655 | 4 | 3
Presentation | 0% | 19/7/2021 | 2021-09-08 | 23 | 4 | Laurie Strode | 10 | 9 | 200 | 150 | 5 | 3
Slides | 0% | 19/7/2021 | 2021-09-08 | 23 | 4 | Alexandra Cuartin | 15 | 10 | 450 | 300 | 4 | 1
Reflective Essay | 0% | 19/7/2021 | 2021-09-08 | 23 | 4 | Wendy Torrance | 20 | 24 | 100 | 100 | 3
[6 empty] | Victor Pascow | 1 | 1
[6 empty] | Alexandra Cuartin | 5 | 4 | 105 | 105 | 5 | 4
[6 empty] | Victor Pascow | 1 | 1
[6 empty] | Victor Pascow | 1 | 1
[7 empty] | 9.5 | 9.5 | 100 | 150 | 4 | 3
[6 empty] | Jason Myers | 3 | 3 | 100 | 150 | 4 | 3
[6 empty] | Jason Myers | 1 | 1
[6 empty] | Alexandra Cuartin | 1 | 1 |  |  | 4 | 4
[6 empty] | Alex Spine | 0.5 | 0.5 |  |  | 4 | 1
[6 empty] | Alexandra Cuartin | 4 | 3 | 150 | 200 | 5 | 2
[6 empty] | Victor Pascow | 15 |  | 250 | 250 | 5 | 1
[6 empty] | Wendy Torrance | 2
[6 empty] | Andy Barclay | 1 |  |  |  | 5 | 1
*Cells calculated automatically